## Slide 1
&
PRIME | H2 2026 ROI PLAN | INTERNAL
01
H2 must add AED 22.0M — a 39% ROI step-up in six months
Two engines carry the number: incremental annualised sales and validated revenue protection. Hiring, retention, productivity and CVM are the capacity that delivers them — not additional revenue lines.
ILLUSTRATIVE PLACEHOLDER DATA - replace with confirmed H1 2026 actuals and H2 2026 targets. As of 26 August 2026. AED millions. ARR = MRC x 12; device value is one-time and is not annualised.
56.5
H1 2026 actual
+15.5
Incremental sales
+6.5
Revenue protection
78.5
H2 2026 target
Bridge from H1 2026 actual to H2 2026 target · AED millions
AED 22.0M
Incremental ROI revenue required in H2 2026
+39%
Step-up on the H1 base of AED 56.5M
+25%
Required output per productive KAM per half
AED 84M
Recurring base sitting in 16 unmanaged portfolios
Notes: Opening message: the number is a 39% step-up in six months, and it splits into exactly two ROI engines. Engine 1 - incremental annualised sales: AED 41.0M in H1 to AED 56.5M in H2 across Mobile, Fixed, Digital & ES and Devices. Device value is one-time and is NOT annualised; it is reported separately so the ARR line stays clean. Engine 2 - revenue protection: AED 15.5M to AED 22.0M of validated retained ARR from accounts that hit a defined churn-risk trigger. The discipline point for leadership: hiring, retention, productivity and CVM are NOT a third revenue line. They are the capacity that makes the first two achievable. Counting them separately would double count the same dirham. Rounding: bar values are rounded to one decimal; the bridge reconciles exactly to AED 22.0M.

## Slide 2
&
WHERE THE GROWTH COMES FROM
02
Six levers close the AED 22.0M gap, each with one owner
Sales engine AED 15.5M · Protection engine AED 6.5M · the contributions reconcile to the gap, with no lever counted twice.
ILLUSTRATIVE PLACEHOLDER DATA - replace with confirmed H1 2026 actuals and H2 2026 targets. As of 26 August 2026. AED millions. ARR = MRC x 12; device value is one-time and is not annualised.
Chart: 
| Talent retention & continuity | Account management & save plays | Zero-vacancy portfolio coverage | KAM productivity operating system | Digital campaigns & CVM acceleration | Sales engine & pipeline discipline
Incremental sales | 0 | 0 | 2.5 | 3.3 | 4.9 | 4.8
Revenue protection | 1.3 | 5.2 | 0 | 0 | 0 | 0
L1
Sales engine & pipeline discipline
Directors (3) · Coverage 3.0x; stale pipeline <15%
+4.8
L6
Digital campaigns & CVM acceleration
Prime + CVM lead · 1,100 digital MQLs/month; 24h KAM SLA
+4.9
L3
KAM productivity operating system
Team Leaders (14) · Selling time 55%; 4.5 opps/KAM/month
+3.3
L5
Zero-vacancy portfolio coverage
Prime Ops + HR · Vacancy <2; time-to-fill 35 days
+2.5
L2
Account management & save plays
Directors + TLs · 90% of Red-tier accounts touched in 10 days
+5.2
L4
Talent retention & continuity
Prime + HRBP · Regretted attrition <=7%; stay interviews 100%
+1.3
Notes: Read the chart left, the accountability right. Two rules keep this honest: 1. No double counting. CVM-attributed revenue is a SOURCE attribution inside Mobile, Fixed, Digital and Devices - it is not a seventh product line. L6 is credited only with the incremental ARR that would not have been created without the campaign engine. 2. Protection is not sales. L2 and L4 recognise retained ARR on accounts with a validated risk trigger; L1, L3, L5 and L6 recognise new ARR. The same dirham never appears in both. Weakest link to call out: L6 at AED 4.9M assumes CVM lead volume roughly triples AND that KAMs act on digital leads within 24 hours. Without the closed loop, the leads convert at today's 9% and this lever under-delivers by roughly half.

## Slide 3
&
THE BINDING CONSTRAINT
03
Capacity is the constraint: +25% output per KAM is required
At H1 productivity the target would need 132 productive KAMs. Even fully staffed we average 105.8 — so the gap must be closed by productivity, coverage and lead flow.
ILLUSTRATIVE PLACEHOLDER DATA - replace with confirmed H1 2026 actuals and H2 2026 targets. As of 26 August 2026. AED millions. ARR = MRC x 12; device value is one-time and is not annualised.
KAM capacity vs. requirement (productive FTE)
Chart: 
| Jul | Aug | Sep | Oct | Nov | Dec
Productive KAM FTE (plan) | 97 | 100 | 104 | 108 | 112 | 114
Required at H1 productivity (132) | 132 | 132 | 132 | 132 | 132 | 132
Vacancy and attrition trajectory (%)
Chart: 
| Jul | Aug | Sep | Oct | Nov | Dec
KAM vacancy rate | 12.5 | 10.8 | 8.3 | 5.8 | 3.3 | 1.7
Rolling 12-month attrition | 20.2 | 19 | 17.5 | 16 | 15 | 14
104 of 120
KAM positions filled today
16 vacant portfolios hold AED 84M of recurring base
AED 427k → 534k
Incremental ARR per productive KAM, per half
+25% — delivered by selling time, next-best-action and lead flow
21% → 14%
Rolling KAM attrition
Regretted attrition 13% → 7%; every exit costs ~4 months of portfolio momentum
Notes: This is the slide that decides whether the plan is credible. The arithmetic: H1 delivered AED 41.0M of incremental ARR on an average 96 productive FTE, i.e. AED 427k per KAM per half. The H2 target of AED 56.5M against an average 105.8 productive FTE requires AED 534k - a 25% uplift. At unchanged productivity we would need 132 productive KAMs, which the approved headcount of 120 cannot supply. So the uplift must come from three sources, not wishful thinking: selling time 41% to 55% (+12%), digital lead flow through CVM (+7%), and solution/AI attach on existing accounts (+6%). Productive FTE is defined as headcount adjusted for vacancy, notice period, leave and new-joiner ramp (month 1 30%, month 2 60%, month 3 85%, month 4 100%). Ask HR to confirm the vacancy and attrition baselines before this goes to CBO.

## Slide 4
&
EXECUTION, GOVERNANCE AND DECISIONS
04
Three waves, one weekly rhythm, three decisions needed now
Every initiative has an owner, a leading indicator and a stop/scale review. The build is back-loaded, so the first 30 days decide the half.
ILLUSTRATIVE PLACEHOLDER DATA - replace with confirmed H1 2026 actuals and H2 2026 targets. As of 26 August 2026. AED millions. ARR = MRC x 12; device value is one-time and is not annualised.
DAYS 0–30
Stabilise the base
Zero-vacancy sprint: 16 offers out, bridge coverage on every orphan portfolio within 5 working days
Churn Early-Warning Index live in Power Apps; Red/Amber tiering on 100% of the managed base
Pipeline hygiene reset: stage gates, mandatory next action, ECD clean-up to >95% data quality
Baseline lock with Finance: ARR, protection and churn definitions signed off
DAYS 31–60
Lift the engine
Save-play playbook deployed; 90% of Red accounts touched within 10 days of trigger
Admin-elimination backlog: remove 6 hours/KAM/week of non-selling work
Always-on CVM journeys 3 → 9; digital lead-to-KAM SLA of 24 hours enforced
AI Opportunity Spotting rollout: every KAM certified, 2 VALUE-scored leads each
DAYS 61–90
Scale what works
Reallocate portfolios on exposure-weighted coverage; retire the bridge pool
Stop/scale review: fund the top three plays, kill anything below 1.5x return
Retention: stay interviews for the top quartile, career lattice and earn-back incentive live
Forecast moves to evidence bands (commit / best / upside) at Director level
Monthly build to target (AED M, incremental vs H1 run-rate)
Chart: 
| Jul | Aug | Sep | Oct | Nov | Dec
Incremental sales | 1.2 | 1.8 | 2.4 | 3 | 3.4 | 3.7
Revenue protection | 0.6 | 0.8 | 1 | 1.2 | 1.4 | 1.5
DECISIONS REQUIRED
1
Release the 16 vacant KAM requisitions with a 35-day time-to-fill SLA and a standing 3-person bridge pool.
2
Approve AED 6.5M of enabling spend against AED 22.0M of benefit — 2.4x net return, payback in month 4.
3
Sign off the protection methodology with Finance so retained ARR is recognised on evidence, not on claim.
Notes: Operating rhythm behind the waves: - Weekly (Mon, 45 min): Director war room - coverage, Red-tier churn saves, top 20 opportunities, blockers with named owners. - Weekly (Wed): TL 1:1s on the 10-4-2-1 KAM rhythm (10 accounts touched, 4 discovery conversations, 2 qualified opportunities, 1 closure). - Monthly: ROI Ledger review with Finance - every claimed dirham carries an evidence status. - Monthly: people review - vacancy, ramp, flight risk, regretted attrition. - Quarterly: stop/scale on initiatives and portfolio rebalancing. The three asks are the ones I cannot resolve inside Prime. Number 3 matters most: without an agreed protection methodology, the AED 22.0M protection line will be challenged at year end and the whole ROI number becomes contestable. Top failure modes: (1) hiring slips and the productivity ask becomes impossible; (2) CVM lead flow arrives but the 24-hour KAM SLA is not enforced; (3) protection is claimed without evidence and is written back.